## High Level Task_Table
Sl.No. | App Features | Corresponding Backend Function | KM - Comments | UI | Backend
1 | Setting up environment for development: • Getting JS specific files and plugins from GitHub • IDE • Using Gits for version control |  |  | 8hours
2 | Unit TDD tool - Jasmine : Installation along with test cases writing for 2 user stories with respect to Sprint1 |  |  | 8hours
3 | Understanding API Specifications Dependency with the backend services developed using NodeJS |  |  | 8hours
4 | Home Screen • Background video - Using JavaScript • Adding animated text as specified in the UX for Home Screen - Using JavaScript |  |  | 8hours
5 | Home Screen (Contd.) • Adding menu tab controls - Using HTML & JavaScript • Adding side panel control - Using JavaScript and displaying a completely new page using HTML5 & JavaScript • Link to Home screen from the above new screen |  |  | 8hours
6 | Menu Progress Bar - Using JavaScript • Need to show the progress bar when user scroll down. • Need to show the progress bar based on the ideas submitted. |  |  | 8hours
7 | Login Screen • Backend API Integration. • Validations using JS. |  |  | 8hours
8 | Registration Screen • Backend API Integration. • Validations using JS. |  |  | 8hours
9 | Share my ideas • Live Progress bar based on the idea submitted using JS and HTML |  |  | 8hours
10 | Share my ideas • Drag and Drop feature for uploading files from physical system to server through browser. |  |  | 8hours