## High Level Task_Table
Sl.No. | Task Details Backend | Duration | Remarks
1 | Setting up environment for development: • Using Git for version control. • Creating the folder structure for development. • Overview of GIT. | 8hours
2 | Writing unit test cases using mocha and chai for 2 user stories. Creating schema and collection for ideaSubmission in local mongoDB. | 8hours
3 | Creating api for posting the idea_details data. | 8hours
4 | Understanding Node Js SDK usage for AWS cognito for authentication. | 8hours
5 | Integration of Node Js SDK for authentication using AWS Cognito service. | 8hours
6 | Integration of Node Js SDK for authentication using AWS Cognito service. | 8hours
7 | Integration of Node Js SDK for authentication using AWS Cognito service. | 8hours
8 | Creation of api for login screen. | 8hours
9 | Understanding of session token and implementing. | 8hours